## 00 Cover
THE TRUE TROOP CONSULTING · METRO PLAZA FOUNDATION CONSTRUCTION · TT-CR-01
Answer workbook
Deliverable D1. Paste your P6 Activity Table into the three dump sheets (07 to 09); sheets 10, 12 and 13 fill themselves. Type only where a cell is yellow. Black text is a formula: leave it alone.
Student details
First name
Surname
Email
| Cohort | Cohort 4
Pod group number
Pod name
Date submitted
How to use this workbook
| Step 1 | Read sheets 01 to 06. They are the brief in Excel: calendar and settings, the activities with their logic and resources, the resource dictionary, the material quantities and both site reports. You never type on them.
| Step 2 | Build the baseline in P6. Reconcile the budget to the pound before you save and assign BL1 (sheet 10 shows the difference against the brief for every activity).
| Step 3 | In P6, create the layout described at the top of sheet 07 (18 columns, in that order). Select all activities in the Activity Table, copy, and paste into sheet 07 at cell A7. Sheet 10 fills itself.
| Step 4 | Sheet 11 is the same table again, blank. Write your own VLOOKUP formulas against sheet 07 to fill it. The last column tells you whether each VLOOKUP agrees with sheet 10.
| Step 5 | Apply the Week 1 site report (sheet 05), schedule to 10/07/2025 09:00, copy the Activity Table and paste into sheet 08. Sheet 12 fills itself. Repeat for Week 2 with sheet 06, sheet 09 and sheet 13.
| Step 6 | Read the Resource Usage Profile for R004 Carpenters at baseline and complete sheet 14.
| Step 7 | Answer the three reflection questions on sheets 12 and 13 and write the narrative (D3) on sheet 15, within the word limits.
| Step 8 | Open sheet 16, confirm D1 to D4, tick the declaration, save with the file name shown there and upload with your Week 2 XER and screenshots.
Legend
| Yellow cell, blue text | You type or paste here
| Black text | Formula. Leave alone.
| Cream band | Given in the brief, for reference
| Gold tab | Brief sheets (01 to 06). Grey tabs are the P6 dump sheets (07 to 09). Navy tabs are your answers (10 to 16).
Progress tracker
| Section | Done of required
| Baseline pasted (sheet 07) | 0 of 22
| Week 1 pasted (sheet 08) | 0 of 22
| Week 2 pasted (sheet 09) | 0 of 22
| VLOOKUP practice (sheet 11) | 2 of 132
| Carpenters (sheet 14) | 0 of 25
| Narrative (sheet 15) | 0 of 5
| Overall completion | 0.8772%
Proof numbers at a glance
| Measure | Your figure
| Budget at completion | 371621
Baseline finish
Week 1 forecast finish
Week 1 SPI
Week 1 CPI
Week 2 forecast finish
Week 2 SPI
Week 2 CPI
| Week 2 EAC | 0
| Carpenter peak demand (h/day) | 0

## 01 Settings
THE TRUE TROOP CONSULTING · METRO PLAZA FOUNDATION CONSTRUCTION · TT-CR-01
Calendar and settings
Section 03 of the brief. Set these before you add a single activity. Most reconciliation problems trace back to a calendar or a default that was left alone.
| Setting | Value
| Project ID and name | CFCP-2025-001, Metro Plaza Foundation Construction
| Planned start | Tuesday 01/07/2025
| Calendar | CFCP-2025-001 - Standard Business Hours: Monday to Friday, 09:00 to 17:00, 8 hours a day, no holidays. Project calendar, also the default for resources
| Duration type | Fixed Duration and Units
| Percent complete type | Physical
| Activity type | Task Dependent; A1200 Start Milestone; A1210 Finish Milestone
| Relationships | All Finish to Start, zero lag, no constraints
| Critical activities | Total float less than or equal to 0 h
| Resource settings | Auto compute actuals off; calculate costs from units on; rate type Price / Unit
| Currency | Pounds sterling. The XER files carry the base currency at a rate of 1, so read every figure as £
| Earned value | Activity % Complete (Physical) for earned value; ETC = remaining cost
| Data date, Week 1 | Thursday 10/07/2025 09:00 (progress to close of play Wednesday 09/07/2025)
| Data date, Week 2 | Thursday 17/07/2025 09:00 (progress to close of play Wednesday 16/07/2025)
DATA DATES Site reports progress to close of play on Wednesday. The new data date is Thursday 09:00. Enter the date with its time shown.

## 02 Activities
THE TRUE TROOP CONSULTING · METRO PLAZA FOUNDATION CONSTRUCTION · TT-CR-01
Work breakdown and activities
Section 04 of the brief, Tables 4.1 and 4.2 in full. Durations and assignments are given; the dates are yours to schedule. Budgets are priced live from sheet 03, so you can see the arithmetic behind every figure.
Table 4.1 Work breakdown structure
Code | Node | Contents
MS | Key Milestones | A1200 Notice to Proceed (start), A1210 Foundations Complete (finish)
N | North Sector | CFCP-North-100 to 140
S | South Sector | CFCP-South-100 to 140
E | East Sector | CFCP-East-100 to 140
W | West Sector | CFCP-West-100 to 140
Table 4.2 Activities, logic and resource assignments
ID | Activity | WBS | Dur (d) | Predecessors | Resource 1 | Units | Resource 2 | Units | Resource 3 | Units | Labour hours | Nonlabour hours | Budgeted cost (£) | Unit note
Key Milestones
A1200 | Notice to Proceed (NTP) | MS | 0 | [7 empty] | 0 | 0 | 0 | Start milestone
North Sector
CFCP-North-100 | Site Preparation - North | N | 3 | A1200 | R001 | 288 |  |  |  |  | 288 | 0 | 8064 | R001 in h
CFCP-North-110 | Excavation - North Foundation | N | 4 | CFCP-North-100 | R002 | 64 | R003 | 960 | R008 | 32 | 1024 | 32 | 30240 | R002 in h; R003 in h; R008 in h
CFCP-North-120 | Formwork Setup - North | N | 5 | CFCP-North-110 | R004 | 320 | R012 | 160 |  |  | 320 | 0 | 16320 | R004 in h; R012 in m2
CFCP-North-130 | Rebar Installation - North | N | 3 | CFCP-North-120 | R011 | 8.5 | R005 | 432 |  |  | 432 | 0 | 20185 | R011 in t; R005 in h
CFCP-North-140 | Concrete Pour - North Foundation | N | 2 | CFCP-North-130 | R010 | 85 | R006 | 512 | R007 | 16 | 512 | 16 | 26936 | R010 in CY; R006 in h; R007 in h
South Sector
CFCP-South-100 | Site Preparation - South | S | 2 | A1200 | R001 | 192 |  |  |  |  | 192 | 0 | 5376 | R001 in h
CFCP-South-110 | Excavation - South Foundation | S | 3 | CFCP-South-100 | R002 | 48 | R003 | 720 | R008 | 24 | 768 | 24 | 22680 | R002 in h; R003 in h; R008 in h
CFCP-South-120 | Formwork Setup - South | S | 4 | CFCP-South-110 | R004 | 256 | R012 | 130 |  |  | 256 | 0 | 13132 | R004 in h; R012 in m2
CFCP-South-130 | Rebar Installation - South | S | 2 | CFCP-South-120 | R011 | 6.5 | R005 | 288 |  |  | 288 | 0 | 14165 | R011 in t; R005 in h
CFCP-South-140 | Concrete Pour - South Foundation | S | 2 | CFCP-North-140, CFCP-South-130 | R010 | 70 | R006 | 512 | R007 | 16 | 512 | 16 | 25136 | R010 in CY; R006 in h; R007 in h
East Sector
CFCP-East-100 | Site Preparation - East | E | 3 | A1200 | R001 | 288 |  |  |  |  | 288 | 0 | 8064 | R001 in h
CFCP-East-110 | Excavation - East Foundation | E | 4 | CFCP-East-100 | R002 | 64 | R003 | 960 | R008 | 32 | 1024 | 32 | 30240 | R002 in h; R003 in h; R008 in h
CFCP-East-120 | Formwork Setup - East | E | 5 | CFCP-East-110 | R004 | 320 | R012 | 110 |  |  | 320 | 0 | 14420 | R004 in h; R012 in m2
CFCP-East-130 | Rebar Installation - East | E | 3 | CFCP-East-120 | R011 | 5 | R005 | 432 |  |  | 432 | 0 | 17210 | R011 in t; R005 in h
CFCP-East-140 | Concrete Pour - East Foundation | E | 2 | CFCP-South-140, CFCP-East-130 | R010 | 55 | R006 | 512 | R007 | 16 | 512 | 16 | 23336 | R010 in CY; R006 in h; R007 in h
West Sector
CFCP-West-100 | Site Preparation - West | W | 2 | A1200 | R001 | 192 |  |  |  |  | 192 | 0 | 5376 | R001 in h
CFCP-West-110 | Excavation - West Foundation | W | 3 | CFCP-West-100 | R002 | 48 | R003 | 720 | R008 | 24 | 768 | 24 | 22680 | R002 in h; R003 in h; R008 in h
CFCP-West-120 | Formwork Setup - West | W | 4 | CFCP-West-110 | R004 | 256 | R012 | 175 |  |  | 256 | 0 | 14842 | R004 in h; R012 in m2
CFCP-West-130 | Rebar Installation - West | W | 3 | CFCP-West-120 | R011 | 9.5 | R005 | 288 |  |  | 288 | 0 | 16715 | R011 in t; R005 in h
CFCP-West-140 | Concrete Pour - West Foundation | W | 3 | CFCP-East-140, CFCP-West-130 | R010 | 95 | R006 | 768 | R007 | 24 | 768 | 24 | 36504 | R010 in CY; R006 in h; R007 in h
Key Milestones
A1210 | Foundations Complete | MS | 0 | CFCP-West-140 | [6 empty] | 0 | 0 | 0 | Finish milestone
Budget at completion and total hours | [10 empty] | 9440 | 184 | 371621
Budget by sector (check as you go)
Sector | Budgeted cost (£) | Share | Labour hours
Key Milestones | 0 | 0% | 0
North Sector | 101745 | 27.38% | 2576
South Sector | 80489 | 21.66% | 2016
East Sector | 93270 | 25.1% | 2576
West Sector | 96117 | 25.86% | 2272
CHECK AS YOU GO Baseline finish Friday 01/08/2025. Float on early work: South 6 days, East 4, West 9. If your P6 budget for any activity differs from column N, go back to the resource dictionary and the assignment before you save the baseline. The commonest slips: a calendar left at 24 hours, a material resource priced per hour, or Fixed Units instead of Fixed Duration and Units.

## 03 Resources
THE TRUE TROOP CONSULTING · METRO PLAZA FOUNDATION CONSTRUCTION · TT-CR-01
Resource dictionary
Section 05 of the brief. Twelve resources in three types. The type decides how P6 turns units into money. Sheet 02 prices every activity from this table.
ID | Resource | Type | Default units/day | Limit/day | Price | Unit | Priced per
R001 | Site Crew | Labour | 48 | 96 | 28 | Hour | hour
R002 | Excavator Operator | Labour | 16 | 32 | 35 | Hour | hour
R003 | Labourers | Labour | 80 | 240 | 25 | Hour | hour
R004 | Carpenters | Labour | 64 | 128 | 32 | Hour | hour
R005 | Rebar Workers | Labour | 48 | 144 | 30 | Hour | hour
R006 | Concrete Crew | Labour | 64 | 256 | 28 | Hour | hour
R007 | Concrete Truck | Nonlabour | 8 | 16 | 150 | Hour | hour
R008 | Excavator | Nonlabour | 8 | 16 | 125 | Hour | hour
R009 | Concrete Pump | Nonlabour | 8 | 8 | 0 | Hour | hour
R010 | Ready-Mix Concrete | Material | 8 |  | 120 | Cubic yard | cubic yard
R011 | Reinforcement Steel | Material | 8 |  | 850 | Tonne | tonne
R012 | Formwork Ply and Props | Material | 8 |  | 38 | Square metre | square metre
How each type is costed
Labour and nonlabour (hours): budgeted units = units per day × number in the gang × duration. Cost = units × price per hour. Site Preparation, North: 2 × 48 h/d × 3 d × £28 = £8,064.
Material (quantity): enter the budgeted units straight from sheet 04 and let P6 spread them over the activity. Rebar Installation, North: 8.5 t × £850 = £7,225, plus the fixing gang.
Limits: enter the limit per day on the Units and Prices tab. R004 Carpenters is limited to 128 h a day (two gangs of eight). The baseline asks for 256 h on 10/07 and 11/07. Find that in the Resource Usage Profile before you save the baseline, and say in your report what you would do about it.

## 04 Materials
THE TRUE TROOP CONSULTING · METRO PLAZA FOUNDATION CONSTRUCTION · TT-CR-01
Material quantities
Section 06 of the brief. The budgeted units for the three material resources. They drive the formwork, rebar and concrete pour costs.
Sector | Ready-mix concrete (CY) | Reinforcement steel (t) | Formwork ply and props (m²) | Steel per CY (t) | Sense check
North | 85 | 8.5 | 160 | 0.1 | Near 0.10 t/CY
South | 70 | 6.5 | 130 | 0.092857 | Near 0.10 t/CY
East | 55 | 5 | 110 | 0.090909 | Near 0.10 t/CY
West | 95 | 9.5 | 175 | 0.1 | Near 0.10 t/CY
Total | 305 | 29.5 | 575
SENSE CHECK Steel divided by concrete should sit near 0.10 t per cubic yard on every pad. A pad three times higher is a typing error, not a design. Always sense-check material quantities before you load them; the planner who catches it saves the job the cost of ordering it.

## 05 Week 1 report
THE TRUE TROOP CONSULTING · METRO PLAZA FOUNDATION CONSTRUCTION · TT-CR-01
Week 1 site report
Section 07 of the brief. Progress to close of play on Wednesday 09/07/2025. New data date Thursday 10/07/2025 09:00. Enter nothing for any activity not listed, then set the data date and schedule.
Activity ID | Activity | Status | Actual start | Actual finish | Remaining (d) | Phys % | Resource | Actual units | Remaining units | Unit | What site said
A1200 | Notice to Proceed (NTP) | Completed | 2025-07-01 | 2025-07-01 |  | 100% |  |  |  |  | Completed as planned.
CFCP-North-100 | Site Preparation - North | Completed | 2025-07-01 | 2025-07-07 |  | 100% | R001 Site Crew | 480 | 0 | h | Finished Monday 07/07, two days late: buried obstructions. Site crew booked 480 h against 288 h.
CFCP-South-100 | Site Preparation - South | Completed | 2025-07-01 | 2025-07-02 |  | 100% | R001 Site Crew | 192 | 0 | h | Completed as planned.
CFCP-East-100 | Site Preparation - East | Completed | 2025-07-01 | 2025-07-03 |  | 100% | R001 Site Crew | 288 | 0 | h | Completed as planned.
CFCP-West-100 | Site Preparation - West | Completed | 2025-07-01 | 2025-07-02 |  | 100% | R001 Site Crew | 192 | 0 | h | Completed as planned.
CFCP-West-110 | Excavation - West Foundation | Completed | 2025-07-03 | 2025-07-07 |  | 100% | R002 Excavator Operator | 48 | 0 | h | Completed as planned.
[7 empty] | R003 Labourers | 720 | 0 | h
[7 empty] | R008 Excavator | 24 | 0 | h
CFCP-South-110 | Excavation - South Foundation | Completed | 2025-07-03 | 2025-07-08 |  | 100% | R002 Excavator Operator | 64 | 0 | h | Finished Tuesday 08/07, one day late on a soft spot. Labourers stood down for the extra day.
[7 empty] | R003 Labourers | 720 | 0 | h
[7 empty] | R008 Excavator | 32 | 0 | h
CFCP-East-110 | Excavation - East Foundation | In progress | 2025-07-04 |  | 1 | 90% | R002 Excavator Operator | 64 | 16 | h | 90% dug. One more day needed, with half the labour gang.
[7 empty] | R003 Labourers | 960 | 120 | h
[7 empty] | R008 Excavator | 32 | 8 | h
CFCP-North-110 | Excavation - North Foundation | In progress | 2025-07-08 |  | 3 | 25% | R002 Excavator Operator | 32 | 48 | h | Started Tuesday 08/07. Wet clay: 25% dug in two days, about half the planned output. Three more days needed at full gang.
[7 empty] | R003 Labourers | 480 | 720 | h
[7 empty] | R008 Excavator | 16 | 24 | h
GENERAL No formwork has started: the formwork gang mobilises on Monday 14/07. Enter nothing for any activity not listed. Then set the data date to 10/07/2025 09:00 and schedule.
YOU SHOULD FIND Forecast finish 06/08/2025, three working days late. SPI 0.73, CPI 0.86, estimate at completion £390,677.

## 06 Week 2 report
THE TRUE TROOP CONSULTING · METRO PLAZA FOUNDATION CONSTRUCTION · TT-CR-01
Week 2 site report
Section 08 of the brief. Progress to close of play on Wednesday 16/07/2025. New data date Thursday 17/07/2025 09:00. Enter nothing for any activity not listed, then set the data date and schedule.
Activity ID | Activity | Status | Actual start | Actual finish | Remaining (d) | Phys % | Resource | Actual units | Remaining units | Unit | What site said
CFCP-North-110 | Excavation - North Foundation | Completed | 2025-07-08 | 2025-07-11 |  | 100% | R002 Excavator Operator | 96 | 0 | h | Finished Friday 11/07, a day earlier than last week's forecast, after a second excavator and operator were brought in.
[7 empty] | R003 Labourers | 960 | 0 | h
[7 empty] | R008 Excavator | 48 | 0 | h
CFCP-East-110 | Excavation - East Foundation | Completed | 2025-07-04 | 2025-07-11 |  | 100% | R002 Excavator Operator | 80 | 0 | h | Hit a rock band. Finished Friday 11/07, a day later than last week's forecast.
[7 empty] | R003 Labourers | 1080 | 0 | h
[7 empty] | R008 Excavator | 40 | 0 | h
CFCP-North-120 | Formwork Setup - North | In progress | 2025-07-14 |  | 2 | 60% | R004 Carpenters | 192 | 128 | h | Started Monday 14/07. 60% fixed. Two more days.
[7 empty] | R012 Formwork Ply and Props | 96 | 64 | m2
CFCP-South-120 | Formwork Setup - South | In progress | 2025-07-14 |  | 2 | 50% | R004 Carpenters | 192 | 128 | h | Started Monday 14/07. Half done. Two more days.
[7 empty] | R012 Formwork Ply and Props | 65 | 65 | m2
CFCP-West-120 | Formwork Setup - West | In progress | 2025-07-16 |  | 4 | 10% | R004 Carpenters | 64 | 256 | h | Started Wednesday 16/07 with a second gang. 10% fixed. Four more days.
[7 empty] | R012 Formwork Ply and Props | 18 | 157 | m2
GENERAL East formwork has not started: no carpentry gang free until the North or South gang moves across. Then set the data date to 17/07/2025 09:00 and schedule.
YOU SHOULD FIND Forecast finish 05/08/2025, two working days late. SPI 0.68, CPI 0.89, estimate at completion £390,333. The finish date improved by a day and the SPI fell. Your report must explain why.

## 07 P6 dump BL
THE TRUE TROOP CONSULTING · METRO PLAZA FOUNDATION CONSTRUCTION · TT-CR-01
P6 dump: baseline (BL1 saved, no progress)
Paste here, nothing else. In P6 build a layout called MPFC Export with the 18 columns below in this order, select every activity in the Activity Table, Ctrl+C, then click cell A7 here and Ctrl+V. Dates may paste as text with an A after actual dates: the sheets that read this table allow for it.
P6 columns to display, in order (Activity Table, Columns, Customise):
Activity ID | Activity Name | Activity Status | Original Duration | Remaining Duration | Start | Finish | Actual Start | Actual Finish | Total Float | Physical % Complete | Budgeted Labor Units | Budgeted Nonlabor Units | Budgeted Total Cost | Planned Value Cost | Earned Value Cost | Actual Cost | Remaining Cost

## 08 P6 dump W1
THE TRUE TROOP CONSULTING · METRO PLAZA FOUNDATION CONSTRUCTION · TT-CR-01
P6 dump: Week 1 update, data date 10/07/2025 09:00
Paste here, nothing else. In P6 build a layout called MPFC Export with the 18 columns below in this order, select every activity in the Activity Table, Ctrl+C, then click cell A7 here and Ctrl+V. Dates may paste as text with an A after actual dates: the sheets that read this table allow for it.
P6 columns to display, in order (Activity Table, Columns, Customise):
Activity ID | Activity Name | Activity Status | Original Duration | Remaining Duration | Start | Finish | Actual Start | Actual Finish | Total Float | Physical % Complete | Budgeted Labor Units | Budgeted Nonlabor Units | Budgeted Total Cost | Planned Value Cost | Earned Value Cost | Actual Cost | Remaining Cost

## 09 P6 dump W2
THE TRUE TROOP CONSULTING · METRO PLAZA FOUNDATION CONSTRUCTION · TT-CR-01
P6 dump: Week 2 update, data date 17/07/2025 09:00
Paste here, nothing else. In P6 build a layout called MPFC Export with the 18 columns below in this order, select every activity in the Activity Table, Ctrl+C, then click cell A7 here and Ctrl+V. Dates may paste as text with an A after actual dates: the sheets that read this table allow for it.
P6 columns to display, in order (Activity Table, Columns, Customise):
Activity ID | Activity Name | Activity Status | Original Duration | Remaining Duration | Start | Finish | Actual Start | Actual Finish | Total Float | Physical % Complete | Budgeted Labor Units | Budgeted Nonlabor Units | Budgeted Total Cost | Planned Value Cost | Earned Value Cost | Actual Cost | Remaining Cost

## 10 Baseline
THE TRUE TROOP CONSULTING · METRO PLAZA FOUNDATION CONSTRUCTION · TT-CR-01
Baseline programme (BL1)
Fills itself from sheet 07. Early Start and Early Finish come from Start and Finish, Critical is derived from Total Float, and the two difference columns compare your P6 budget with the brief: they turn green at zero.
Activity ID | Activity | WBS | OD (d) | Early Start | Early Finish | Total Float (d) | Critical | Budgeted Labour Units (h) | Budgeted Nonlabour Units (h) | Budgeted Total Cost (£) | Brief budget (£) | Difference (£) | Brief labour (h) | Labour difference (h)
Key Milestones
A1200 | Notice to Proceed (NTP) | MS | 0 |  |  | n/a | n/a |  |  |  | 0 |  | 0
North Sector
CFCP-North-100 | Site Preparation - North | N | 3 | [7 empty] | 8064 |  | 288
CFCP-North-110 | Excavation - North Foundation | N | 4 | [7 empty] | 30240 |  | 1024
CFCP-North-120 | Formwork Setup - North | N | 5 | [7 empty] | 16320 |  | 320
CFCP-North-130 | Rebar Installation - North | N | 3 | [7 empty] | 20185 |  | 432
CFCP-North-140 | Concrete Pour - North Foundation | N | 2 | [7 empty] | 26936 |  | 512
South Sector
CFCP-South-100 | Site Preparation - South | S | 2 | [7 empty] | 5376 |  | 192
CFCP-South-110 | Excavation - South Foundation | S | 3 | [7 empty] | 22680 |  | 768
CFCP-South-120 | Formwork Setup - South | S | 4 | [7 empty] | 13132 |  | 256
CFCP-South-130 | Rebar Installation - South | S | 2 | [7 empty] | 14165 |  | 288
CFCP-South-140 | Concrete Pour - South Foundation | S | 2 | [7 empty] | 25136 |  | 512
East Sector
CFCP-East-100 | Site Preparation - East | E | 3 | [7 empty] | 8064 |  | 288
CFCP-East-110 | Excavation - East Foundation | E | 4 | [7 empty] | 30240 |  | 1024
CFCP-East-120 | Formwork Setup - East | E | 5 | [7 empty] | 14420 |  | 320
CFCP-East-130 | Rebar Installation - East | E | 3 | [7 empty] | 17210 |  | 432
CFCP-East-140 | Concrete Pour - East Foundation | E | 2 | [7 empty] | 23336 |  | 512
West Sector
CFCP-West-100 | Site Preparation - West | W | 2 | [7 empty] | 5376 |  | 192
CFCP-West-110 | Excavation - West Foundation | W | 3 | [7 empty] | 22680 |  | 768
CFCP-West-120 | Formwork Setup - West | W | 4 | [7 empty] | 14842 |  | 256
CFCP-West-130 | Rebar Installation - West | W | 3 | [7 empty] | 16715 |  | 288
CFCP-West-140 | Concrete Pour - West Foundation | W | 3 | [7 empty] | 36504 |  | 768
Key Milestones
A1210 | Foundations Complete | MS | 0 |  |  | n/a | n/a |  |  |  | 0 |  | 0
Baseline finish (latest Early Finish)
Budget at completion and total units | [7 empty] | 0 | 0 | 0 | 371621 |  | 9440
CHECK AS YOU GO Every sector budget, the baseline finish and the budget at completion are published on the class dashboard. A red difference means your P6 budget for that activity differs from the brief: look at the calendar (8 h/d), the rate type, and Fixed Duration and Units before you save the baseline.

## 11 Baseline VLOOKUP
THE TRUE TROOP CONSULTING · METRO PLAZA FOUNDATION CONSTRUCTION · TT-CR-01 | [15 empty] | Tracker
Baseline, your VLOOKUP practice | [15 empty] | 2
The same table as sheet 10, but you write the formulas. For each yellow cell write a VLOOKUP against sheet 07 (the table is $A$7:$R$46; count the column you need from the header row there). Rows 1 and 2 are worked for you. The last column tells you whether your result agrees with sheet 10. | [15 empty] | 132
Activity ID | Activity | WBS | OD (d) | Early Start | Early Finish | Total Float (d) | Critical | Budgeted Labour Units (h) | Budgeted Nonlabour Units (h) | Budgeted Total Cost (£) | Brief budget (£) | Difference (£) | Brief labour (h) | Labour difference (h) | Agrees with sheet 10
Key Milestones
A1200 | Notice to Proceed (NTP) | MS | 0 |  |  | n/a | n/a |  |  |  | 0 |  | 0 |  | Agree
North Sector
CFCP-North-100 | Site Preparation - North | N | 3 | [7 empty] | 8064 |  | 288
CFCP-North-110 | Excavation - North Foundation | N | 4 | [7 empty] | 30240 |  | 1024
CFCP-North-120 | Formwork Setup - North | N | 5 | [7 empty] | 16320 |  | 320
CFCP-North-130 | Rebar Installation - North | N | 3 | [7 empty] | 20185 |  | 432
CFCP-North-140 | Concrete Pour - North Foundation | N | 2 | [7 empty] | 26936 |  | 512
South Sector
CFCP-South-100 | Site Preparation - South | S | 2 | [7 empty] | 5376 |  | 192
CFCP-South-110 | Excavation - South Foundation | S | 3 | [7 empty] | 22680 |  | 768
CFCP-South-120 | Formwork Setup - South | S | 4 | [7 empty] | 13132 |  | 256
CFCP-South-130 | Rebar Installation - South | S | 2 | [7 empty] | 14165 |  | 288
CFCP-South-140 | Concrete Pour - South Foundation | S | 2 | [7 empty] | 25136 |  | 512
East Sector
CFCP-East-100 | Site Preparation - East | E | 3 | [7 empty] | 8064 |  | 288
CFCP-East-110 | Excavation - East Foundation | E | 4 | [7 empty] | 30240 |  | 1024
CFCP-East-120 | Formwork Setup - East | E | 5 | [7 empty] | 14420 |  | 320
CFCP-East-130 | Rebar Installation - East | E | 3 | [7 empty] | 17210 |  | 432
CFCP-East-140 | Concrete Pour - East Foundation | E | 2 | [7 empty] | 23336 |  | 512
West Sector
CFCP-West-100 | Site Preparation - West | W | 2 | [7 empty] | 5376 |  | 192
CFCP-West-110 | Excavation - West Foundation | W | 3 | [7 empty] | 22680 |  | 768
CFCP-West-120 | Formwork Setup - West | W | 4 | [7 empty] | 14842 |  | 256
CFCP-West-130 | Rebar Installation - West | W | 3 | [7 empty] | 16715 |  | 288
CFCP-West-140 | Concrete Pour - West Foundation | W | 3 | [7 empty] | 36504 |  | 768
Key Milestones
A1210 | Foundations Complete | MS | 0 |  |  | n/a | n/a |  |  |  | 0 |  | 0 |  | Agree
Baseline finish (latest Early Finish)
Budget at completion and total units | [7 empty] | 0 | 0 | 0 | 371621 |  | 9440
HOW TO WRITE IT =VLOOKUP($A6,07 P6 dump BL!$A$7:$R$46,6,FALSE) returns the Start of the activity in A6: column 6 of the dump table is Start. Wrap a date in INT() to drop the time. Use FALSE for an exact match on the Activity ID. Copy the first two rows down and change the column number for each field: Finish 7, Total Float 10, Labor Units 12, Nonlabor Units 13, Total Cost 14.

## 12 Week 1
THE TRUE TROOP CONSULTING · METRO PLAZA FOUNDATION CONSTRUCTION · TT-CR-01
Week 1 update, data date 10/07/2025 09:00
Fills itself from sheet 08. Status, dates, remaining duration and Physical % from the Activity Table; PV, EV, AC and Remaining Cost from the earned value cost columns. Variances, EAC, VAC and the indices are formulas. Then read the position below.
Forecast project finish (Finish of A1210)
Forecast finish date |  |  | Working days late against baseline |  |  |  | Critical path now runs through
Activity ID | Activity | WBS | Status | Actual Start | Actual Finish | Remaining Dur (d) | Phys % | Planned Value (£) | Earned Value (£) | Actual Cost (£) | Remaining Cost / ETC (£) | Schedule Variance (£) | Cost Variance (£) | EAC (£) | VAC (£)
Key Milestones
A1200 | Notice to Proceed (NTP) | MS
North Sector
CFCP-North-100 | Site Preparation - North | N
CFCP-North-110 | Excavation - North Foundation | N
CFCP-North-120 | Formwork Setup - North | N
CFCP-North-130 | Rebar Installation - North | N
CFCP-North-140 | Concrete Pour - North Foundation | N
South Sector
CFCP-South-100 | Site Preparation - South | S
CFCP-South-110 | Excavation - South Foundation | S
CFCP-South-120 | Formwork Setup - South | S
CFCP-South-130 | Rebar Installation - South | S
CFCP-South-140 | Concrete Pour - South Foundation | S
East Sector
CFCP-East-100 | Site Preparation - East | E
CFCP-East-110 | Excavation - East Foundation | E
CFCP-East-120 | Formwork Setup - East | E
CFCP-East-130 | Rebar Installation - East | E
CFCP-East-140 | Concrete Pour - East Foundation | E
West Sector
CFCP-West-100 | Site Preparation - West | W
CFCP-West-110 | Excavation - West Foundation | W
CFCP-West-120 | Formwork Setup - West | W
CFCP-West-130 | Rebar Installation - West | W
CFCP-West-140 | Concrete Pour - West Foundation | W
Key Milestones
A1210 | Foundations Complete | MS
Project totals | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Earned value by sector | [8 empty] | Earned value summary
Sector | BAC (£) | PV (£) | EV (£) | AC (£) | SV (£) | CV (£) | SPI | CPI
North Sector | 101745 | 0 | 0 | 0 | 0 | 0 |  |  | Budget at completion (BAC) | [5 empty] | 371621
South Sector | 80489 | 0 | 0 | 0 | 0 | 0 |  |  | Planned value (PV) | [5 empty] | 0
East Sector | 93270 | 0 | 0 | 0 | 0 | 0 |  |  | Earned value (EV) | [5 empty] | 0
West Sector | 96117 | 0 | 0 | 0 | 0 | 0 |  |  | Actual cost (AC) | [5 empty] | 0
Project | 371621 | 0 | 0 | 0 | 0 | 0 |  |  | Schedule variance (SV = EV - PV) | [5 empty] | 0
[9 empty] | Cost variance (CV = EV - AC) | [5 empty] | 0
[9 empty] | Estimate to complete (ETC) | [5 empty] | 0
[9 empty] | Estimate at completion (EAC = AC + ETC) | [5 empty] | 0
[9 empty] | Variance at completion (VAC = BAC - EAC) | [5 empty] | 0
Schedule performance index (SPI = EV / PV)
Cost performance index (CPI = EV / AC)
To-complete performance index (TCPI to BAC)
EAC if the CPI holds (BAC / CPI)
Read the position
In one sentence, is the project ahead or behind, and by how much?
Which sector carries the worst SPI, and why does the project figure hide it?
What does the CPI tell the client about the final cost?

## 13 Week 2
THE TRUE TROOP CONSULTING · METRO PLAZA FOUNDATION CONSTRUCTION · TT-CR-01
Week 2 update, data date 17/07/2025 09:00
Fills itself from sheet 09. Status, dates, remaining duration and Physical % from the Activity Table; PV, EV, AC and Remaining Cost from the earned value cost columns. Variances, EAC, VAC and the indices are formulas. Then read the position below.
Forecast project finish (Finish of A1210)
Forecast finish date |  |  | Working days late against baseline |  |  |  | Critical path now runs through
Activity ID | Activity | WBS | Status | Actual Start | Actual Finish | Remaining Dur (d) | Phys % | Planned Value (£) | Earned Value (£) | Actual Cost (£) | Remaining Cost / ETC (£) | Schedule Variance (£) | Cost Variance (£) | EAC (£) | VAC (£)
Key Milestones
A1200 | Notice to Proceed (NTP) | MS
North Sector
CFCP-North-100 | Site Preparation - North | N
CFCP-North-110 | Excavation - North Foundation | N
CFCP-North-120 | Formwork Setup - North | N
CFCP-North-130 | Rebar Installation - North | N
CFCP-North-140 | Concrete Pour - North Foundation | N
South Sector
CFCP-South-100 | Site Preparation - South | S
CFCP-South-110 | Excavation - South Foundation | S
CFCP-South-120 | Formwork Setup - South | S
CFCP-South-130 | Rebar Installation - South | S
CFCP-South-140 | Concrete Pour - South Foundation | S
East Sector
CFCP-East-100 | Site Preparation - East | E
CFCP-East-110 | Excavation - East Foundation | E
CFCP-East-120 | Formwork Setup - East | E
CFCP-East-130 | Rebar Installation - East | E
CFCP-East-140 | Concrete Pour - East Foundation | E
West Sector
CFCP-West-100 | Site Preparation - West | W
CFCP-West-110 | Excavation - West Foundation | W
CFCP-West-120 | Formwork Setup - West | W
CFCP-West-130 | Rebar Installation - West | W
CFCP-West-140 | Concrete Pour - West Foundation | W
Key Milestones
A1210 | Foundations Complete | MS
Project totals | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Earned value by sector | [8 empty] | Earned value summary
Sector | BAC (£) | PV (£) | EV (£) | AC (£) | SV (£) | CV (£) | SPI | CPI
North Sector | 101745 | 0 | 0 | 0 | 0 | 0 |  |  | Budget at completion (BAC) | [5 empty] | 371621
South Sector | 80489 | 0 | 0 | 0 | 0 | 0 |  |  | Planned value (PV) | [5 empty] | 0
East Sector | 93270 | 0 | 0 | 0 | 0 | 0 |  |  | Earned value (EV) | [5 empty] | 0
West Sector | 96117 | 0 | 0 | 0 | 0 | 0 |  |  | Actual cost (AC) | [5 empty] | 0
Project | 371621 | 0 | 0 | 0 | 0 | 0 |  |  | Schedule variance (SV = EV - PV) | [5 empty] | 0
[9 empty] | Cost variance (CV = EV - AC) | [5 empty] | 0
[9 empty] | Estimate to complete (ETC) | [5 empty] | 0
[9 empty] | Estimate at completion (EAC = AC + ETC) | [5 empty] | 0
[9 empty] | Variance at completion (VAC = BAC - EAC) | [5 empty] | 0
Schedule performance index (SPI = EV / PV)
Cost performance index (CPI = EV / AC)
To-complete performance index (TCPI to BAC)
EAC if the CPI holds (BAC / CPI)
Read the position
The finish date improved by a day and the SPI fell. Explain why in plain English.
Which sector is now driving the critical path, and what does its SPI say?
Is the EAC credible? Compare EAC = AC + ETC with BAC / CPI.
PV, EV and AC against BAC at both data dates
Data date | PV (£) | EV (£) | AC (£) | BAC (£)
Week 1, 10/07/2025 | 0 | 0 | 0 | 371621
Week 2, 17/07/2025 | 0 | 0 | 0 | 371621

## 14 Carpenters
THE TRUE TROOP CONSULTING · METRO PLAZA FOUNDATION CONSTRUCTION · TT-CR-01 | [5 empty] | Tracker
Resource profile, R004 Carpenters | [5 empty] | 0
From the Resource Usage Profile at baseline, daily, units in hours. Enter the budgeted demand for each working day; the sheet compares it with the limit and flags the overallocation. | [5 empty] | 25
Limit per day (h), from sheet 03 |  | 128
Days over the limit |  | 0
Peak demand (h/day) |  | 0
Working day | Date | Budgeted units (h) | Over limit (h) | Gangs needed | Flag
1 | 2025-07-01
2 | 2025-07-02
3 | 2025-07-03
4 | 2025-07-04
5 | 2025-07-07
6 | 2025-07-08
7 | 2025-07-09
8 | 2025-07-10
9 | 2025-07-11
10 | 2025-07-14
11 | 2025-07-15
12 | 2025-07-16
13 | 2025-07-17
14 | 2025-07-18
15 | 2025-07-21
16 | 2025-07-22
17 | 2025-07-23
18 | 2025-07-24
19 | 2025-07-25
20 | 2025-07-28
21 | 2025-07-29
22 | 2025-07-30
23 | 2025-07-31
24 | 2025-08-01
What would you do about it? (two or three sentences; this feeds your D3 narrative)

## 15 Narrative
THE TRUE TROOP CONSULTING · METRO PLAZA FOUNDATION CONSTRUCTION · TT-CR-01 |  |  |  | Tracker
Narrative (D3) |  |  |  | 0
One page in plain English for a client who does not use P6. Write in the yellow cells; the word count updates as you type. Keep to the limits. |  |  |  | 5
0
Question | Your answer | Words | Limit
What happened in the first two weeks? |  | 0 | 120
Where is the critical path now, and what moved it? |  | 0 | 100
Why did the SPI fall while the finish date improved? |  | 0 | 120
What would you do about the carpenters? |  | 0 | 100
What should the client expect at completion? |  | 0 | 80
Total words |  | 0 | 520

## 16 Submit
THE TRUE TROOP CONSULTING · METRO PLAZA FOUNDATION CONSTRUCTION · TT-CR-01
Submit
Four deliverables, one upload. Confirm each line, tick the declaration, then save with the file name shown and upload through the cohort group before the date your tutor gives.
Item | Deliverable | Status | How it is judged
D1 | Answer workbook: every yellow cell filled, both dumps pasted, VLOOKUP practice complete | 1% done | The progress tracker on sheet 00 reaches 100%
D2 | Your Week 2 XER, exported from P6 with BL1 assigned as the project baseline |  | You confirm the export: type Y
D3 | One-page narrative on sheet 15, within the word limits | Incomplete | Five answers, none over its limit
D4 | Two screenshots: the Resource Usage Profile for R004 at baseline, and the earned value columns at Week 2 |  | You confirm the screenshots: type Y
File name and declaration
| Save this workbook as | Surname_TT-CR-01_Answers.xlsx
Submitted by
Pod
| Declaration: this is my own work, built in my own copy of P6, and I have not shared my login or my files with anyone. Type Y to confirm. |  | Required before upload
| Date | 0
Not ready: check the lines above.